## Risk Register
Risk Register For Project: | Great Things |  |  |  | 0 |  |  |  |  | 0
Project Manager: | A. Kajavatan |  |  |  | 0 |  |  |  |  | 0
Version Date: | YYYY-MM-DD | [8 empty] | 0
|  | Before Response Planning |  |  |  |  | After Response Planning
Risk | Risk Statement | P% | T (d) | $K | P x T | P x $ | P% | T (d) | $K | P x T | P x $ | Owner | Trigger | Response Plan | Backup Plan | Resolution Date
Approval delays | If the approval is not complete in the planned four week time frame, the subsequent work will have to be suspended, causing schedule and budget impacts. | 60% | 25 | 125 | 15 | 75 | 30% | 15 | 75 | 4.5 | 22.5 | B. Baker | Weekly updates indicate delays in processing. | Highlight to senior management to increase prioritization. | Proceed with work that might have to be discarded. | 20XX-MM-DD
Team turnover |  |  |  |  | 0 | 0 |  |  |  | 0 | 0
Resource availability |  |  |  |  | 0 | 0 |  |  |  | 0 | 0
Vendor issues |  |  |  |  | 0 | 0 |  |  |  | 0 | 0
Procurement delays |  |  |  |  | 0 | 0 |  |  |  | 0 | 0
Requirements changes |  |  |  |  | 0 | 0 |  |  |  | 0 | 0
“Problems at end” |  |  |  |  | 0 | 0 |  |  |  | 0 | 0
Development problems |  |  |  |  | 0 | 0 |  |  |  | 0 | 0
Total Risk Budget: |  |  |  |  | 15 | 75 |  |  |  | 4.5 | 22.5
Use
CODING: White cells are for user entry, gray cells are for results.
RISKS (MORE): If you insert rows for more risks, make sure you copy the formulas from an existing row into the PxT and PX$ columns.
RISKS (LESS): You can delete rows if not needed.
BEFORE & AFTER RESPONSE PLANNING: This register shows the risk calculations for both before and after response planning, so management can see how much the risks improved during project planning. As the project progresses, it is common to hide the columns for before planning, or make a copy of this sheet and then delete those columns in the working copy used as execution proceeds.
SECONDARY RISKS: For larger projects you sometimes also include secondary risks, the risks to the response plan solutions.
SECOND LAST ROW: The second last row, above the last row Total Risk Budget, is blank, so the register can be sorted, for example by the After Risk Planning column Px$, without affecting the last row.
.